## 总ProgressProgress Chart
绵阳市二环路十五Contract段ConstructionProgress横道图
序 号 | 工程Project Name | Quantity
|  |  |  | 2010Year | [11 empty] | 2011Year | [35 empty] | Notes
|  |  |  | September |  |  | October |  |  | November |  |  | December |  |  | January |  |  | February |  |  | 3Month份 |  |  | 4Month份 |  |  | 5Month份 |  |  | 6Month份 |  |  | 7Month份 |  |  | 8Month份 |  |  | September |  |  | October |  |  | November |  |  | December
|  | Unit | Quantity | 10 | 10 | 10 | 10 | 10 | 11 | 10 | 10 | 10 | 10 | 10 | 11 | 10 | 10 | 11 | 10 | 10 | 8 | 10 | 10 | 11 | 10 | 10 | 10 | 10 | 10 | 11 | 10 | 10 | 10 | 10 | 10 | 11 | 10 | 10 | 11 | 10 | 10 | 10 | 10 | 10 | 11 | 10 | 10 | 10 | 10 | 10 | 11
1 | Construction准备 | 项 | 1 | [48 empty] | 2010Year9Month22Day～2010Year9Month27Day
2 | K27+212-K28+737道路改造工程 | 项 | 1 | [48 empty] | 2010Year9Month28Day～2011Year2Month3Day
3 | K24+500-K27+212道路土石方工程 | 项 | 1 | [48 empty] | 2010Year9Month28Day～2011Year8Month20Day
4 | K24+500-K27+212道路挡墙、护坡工程 | 项 | 1 | [48 empty] | 2011Year2Month10Day～2011Year7Month10Day
5 | K24+500-K27+212道路工程（垫层及匝道） | 项 | 1 | [48 empty] | 2011Year5Month20Day～2011Year9Month30Day
6 | 地道、箱涵工程 | 项 | 1 | [48 empty] | 2010Year10Month26Day～2011Year2Month10Day
7 | K24+500-K27+212道路排水工程（排水管及检查井） | 项 | 1 | [48 empty] | 2010Year10Month20Day～2011Year9Month12Day
8 | K24+500-K27+212道路路面工程 | 项 | 1 | [48 empty] | 2011Year8Month20Day～2011Year11Month30Day
9 | 桥梁桩基工程 | 项 | 1 | [48 empty] | 2010Year10Month9Day～2011Year4Month10Day
10 | 桥梁墩柱及盖梁等工程 | 项 | 1 | [48 empty] | 2011Year3Month15Day～2011Year10Month15Day
11 | 箱梁现浇工程 | 项 | 1 | [48 empty] | 2011Year6Month10Day～2011Year11Month20Day
12 | 桥梁防护工程 | 项 | 1 | [48 empty] | 2011Year10Month21Day～2011Year11Month30Day
13 | 收尾 | 项 | 1 | [48 empty] | 2011Year12Month1Day～2011Year12Month22Day
洛阳路桥建设集团Company绵阳市二环路十五Contract段Project部 工程部制

## ConstructionProgressPlan（周）
绵阳市二环路十五Contract段ConstructionProgress横道图
序 号 | 工程Project Name | Quantity |  | ContractDuration450天，ProgressPlanned若受拆迁等因素影响，Duration相应顺延。
|  |  |  | 2010Year | [15 empty] | 2011Year | [47 empty] | Notes
|  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | 3Month份 |  |  |  | 4Month份 |  |  |  | 5Month份 |  |  |  | 6Month份 |  |  |  | 7Month份 |  |  |  | 8Month份 |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
|  | Unit | Quantity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64
一 | 道排工程
路基土石方工程
1 | Road Excavation | m3 | 239438 | [64 empty] | 2010Year9Month22Day～2010Year9Month27Day
2 | 挖Normal道路石方 | m3 | 200163 | [64 empty] | 2010Year9Month28Day～2011Year2Month3Day
3 | 清除表土 | m3 | 46897 | [64 empty] | 2010Year9Month28Day～2011Year8Month20Day
4 | 清除淤泥、流沙 | m3 | 3486 | [64 empty] | 2011Year2Month10Day～2011Year7Month10Day
5 | 利用Earth Backfill | m3 | 163334 | [64 empty] | 2011Year5Month20Day～2011Year9Month30Day
6 | 利用石方回填 | m3 | 200163 | [64 empty] | 2010Year10Month26Day～2011Year2Month10Day
7 | 道路回填砂砾石 | m3 | 9580 | [64 empty] | 2010Year10Month20Day～2011Year9Month12Day
8 | 余方弃置(基本运距) | m3 | 126487 | [64 empty] | 2011Year8Month20Day～2011Year11Month30Day
9 | 余方弃置(增运2km) | m3 | 8180.25 | [64 empty] | 2010Year10Month9Day～2011Year4Month10Day
10 | Excess Disposal (9km) | m3 | 118306.75 | [64 empty] | 2011Year3Month15Day～2011Year10Month15Day
| 路面结构工程（K24+000-K27+212.294） | [66 empty] | 2011Year6Month10Day～2011Year11Month20Day
1 | 路床整形碾压 | m2 | 102303 | [64 empty] | 2011Year10Month21Day～2011Year11Month30Day
2 | Shoulder Rolling | m2 | 12756.42 | [64 empty] | 2011Year12Month1Day～2011Year12Month22Day
3 | 主车道路平石 | m | 5924
4 | 主车道路缘石 | m | 4804
5 | 辅车道路平石 | m | 3239
6 | 辅车道路缘石 | m | 1446
7 | 人行道路缘石 | m | 1793
8 | 人行道嵌边石 | m | 1731
9 | 横向φ75PVC管 | m | 1596
10 | 纵向排水管φ100 | m | 3772
11 | DN100钢套管 | m | 1596
12 | Medium央分隔带、侧分带种植土回填 | m3 | 8180.25
13 | Medium央分隔带、侧分带防渗土工布 | m2 | 9896.24
14 | Medium央分隔带、侧分带碎石盲沟 | m | 3772
15 | 填挖交界处碎石盲沟 | m | 350
16 | Sidewalk Paving | m2 | 3522
17 | Sidewalk Paving | m2 | 1076
18 | C20 Permeable Base | m2 | 4598
19 | Gravel Base Course | m2 | 4598
20 | C15混凝土基座 | m3 | 43
21 | 防撞护栏C30混凝土基础 | m3 | 218.24
22 | 土工格栅 | m2 | 5660
23 | 防撞护栏 | m | 760.4
24 | Rebar Installation | t | 10
25 | Rebar Installation | t | 30.58
道路改造工程（K27+212.294-K28+737.937）
1 | Road Excavation | m3 | 4800
2 | 利用Earth Backfill | m3 | 1210
3 | 余方弃置(基本运距) | m3 | 3590
4 | Excess Disposal (9km) | m3 | 3590
5 | Shoulder Rolling | m2 | 12400
6 | Sidewalk Paving | m2 | 12400
7 | C20 Permeable Base | m2 | 12400
8 | Gravel Base Course | m2 | 12400
9 | Medium央分隔带路缘石 | m | 302.5
10 | 人行道路缘石 | m | 3052
11 | 人行道嵌边石 | m | 3052
重力式挡墙
1 | Trench Excavation | m3 | 2827.2
2 | Trench Backfill | m3 | 1403
3 | 余方弃置(基本运距) | m3 | 1425
4 | Excess Disposal (9km) | m3 | 1425
5 | 回填砂卵石 | m3 | 843.6
6 | 回填块石或卵石 | m3 | 433.2
7 | C20片石砼墙身 | m3 | 190
8 | Graded Gravel Filter | m3 | 34.2
9 | Clay Seal Layer、隔水层 | m3 | 68.4
10 | φ100PVC管 | m | 42
11 | φ10cm弹式软管 | m | 158
12 | Settlement Joint | m | 21
悬臂式挡墙
1 | Trench Excavation | m3 | 13445
2 | Trench Backfill | m3 | 5901
3 | 余方弃置(基本运距) | m3 | 7540.6
4 | Excess Disposal (9km) | m3 | 7540.6
5 | Foundation Sand Backfill | m3 | 4442.66
6 | Foundation Rock Backfill | m3 | 2094.72
7 | C10 Concrete Base | m3 | 227.16
8 | C30现Concrete Pour墙身 | m3 | 1848
9 | Graded Gravel Filter | m3 | 428
10 | Clay Seal Layer | m3 | 1513.58
11 | DN50PVC管 | m | 69
12 | Settlement Joint | m | 165.07
13 | Rebar Installation | t | 174.48
（六） | 扶壁式挡墙
1 | Trench Excavation | m3 | 1684.62
2 | Trench Backfill | m3 | 600
3 | 余方弃置(基本运距) | m3 | 1085
4 | Excess Disposal (9km) | m3 | 1085
5 | Foundation Sand Backfill | m3 | 586.2
6 | Foundation Rock Backfill | m3 | 270.6
7 | C10 Concrete Base | m3 | 33.22
8 | C30现Concrete Pour墙身 | m3 | 497.25
9 | Graded Gravel Filter | m3 | 107
10 | Clay Seal Layer | m3 | 15.6
11 | DN50PVC管 | m | 12.6
12 | Settlement Joint | m | 47.07
13 | Rebar Installation | t | 6.47
14 | Rebar Installation | t | 40.1
（七） | 植被混凝土护坡
1 | 平台喷射混凝土封面 | m3 | 880
2 | Φ14锚杆支护 | m | 33726
（八） | 网格护坡
1 | M7.5 Mortar Rubble | m3 | 189.8
（九） | 截水沟
1 | Trench Excavation & Haul | m3 | 1075.7
2 | M7.5 Mortar Rubble | m3 | 733.3
（十） | 排水沟
1 | Trench Excavation & Haul | m3 | 3788.5
2 | M7.5 Mortar Rubble | m3 | 2768.5
（十一） | 浅碟形边沟
1 | Trench Excavation & Haul | m3 | 1892
2 | M7.5 Mortar Rubble | m3 | 1248.72
3 | 碎石盲沟 | m | 1720
4 | 预制混凝土盖板 | m3 | 149.64
5 | 防渗土工布 | m2 | 5607.2
6 | 黑色三维网 | m2 | 7585.2
7 | 种植土回填 | m3 | 2167.2
（十二） | LB-M52型生态护坡
1 | 0.4mm厚阻水膜 | m2 | 2544.6
2 | C20混凝土基础 | m3 | 856.38
（十三） | 排水工程
1 | Trench Excavation | m3 | 8184.4
2 | Trench Backfill | m3 | 3494.33
3 | 沟槽回填砂卵石 | m3 | 5863.26
4 | Excess Disposal (1km) | m3 | 12248.5
5 | Excess Disposal (9km) | m3 | 12248
6 | 井周回填水稳碎石 | m3 | 1898.17
7 | d300Ⅱ混凝土平口雨水管道铺设 | m | 401
8 | d500HDPE双壁波纹雨水管 | m | 917.51
9 | d600Ⅱ混凝土承插雨水管道铺设 | m | 1381.77
10 | d800Ⅱ混凝土承插雨水管道铺设 | m | 297
11 | d1000Ⅱ混凝土承插雨水管道铺设 | m | 150
12 | d500HDPE双壁波纹污水管 | m | 73
13 | d600Ⅱ混凝土承插污水管道铺设 | m | 952
14 | d800Ⅱ混凝土承插污水管道铺设 | m | 115
15 | DN150UPVC排水管 | m | 153.5
16 | 污水混凝土检查井φ1250 | 座 | 11
17 | 污水混凝土检查井φ1500 | 座 | 4
18 | 污水混凝土沉泥井φ1250 | 座 | 8
19 | 雨水混凝土检查井φ1000 | 座 | 74
20 | 雨水混凝土检查井φ1250 | 座 | 10
21 | 雨水混凝土检查井φ1500 | 座 | 4
22 | 雨水混凝土沉泥井φ1000 | 座 | 15
23 | 雨水混凝土沉沙井φ1000 | 座 | 5
24 | 雨水混凝土跌水井φ1000 | 座 | 2
25 | 污水混凝土检查支管井φ1000 | 座 | 7
26 | 雨水混凝土检查支管井φ1000 | 座 | 4
27 | 雨水双蓖井 | 座 | 104
（十四） | 3#矩形明沟2.0*1.5
1 | Excavation | m3 | 389.664
2 | Fill | m3 | 155.36
3 | Excess Disposal (1km) | m3 | 234.3
4 | Excess Disposal (9km) | m3 | 234.3
5 | M10 Mortar MU30 Rubble | m3 | 234.3
（十五） | 2#、4#矩形明沟5.0*2.0
1 | Excavation | m3 | 3051.5
2 | Fill | m3 | 1826.6
3 | Excess Disposal (1km) | m3 | 1226.88
4 | Excess Disposal (9km) | m3 | 1226.88
5 | M10 Mortar MU30 Rubble | m3 | 1226.88
（十六） | 3#钢筋砼箱涵5.0*3.0
1 | Excavation | m3 | 2469.26
2 | Gravel Backfill | m3 | 1158.89
3 | Excess Disposal (1km) | m3 | 3246.89
4 | Excess Disposal (9km) | m3 | 3246.89
5 | C20 Concrete Base | m3 | 81
6 | C30 Box Culvert | m3 | 745.2
7 | Rebar Installation | t | 153.862
8 | 涵洞耳墙 | m3 | 75.46
9 | 洞口帽石 | m3 | 1.89
10 | 浆砌块石护底 | m3 | 12.45
11 | Settlement Joint | m | 153
（十七） | 4#双孔钢筋砼箱涵2*2.5*2.0
1 | Excavation | m3 | 754.94
2 | Gravel Backfill | m3 | 211.63
3 | Excess Disposal (1km) | m3 | 941.81
4 | Excess Disposal (9km) | m3 | 941.81
5 | C20 Concrete Base | m3 | 62.22
6 | C30 Box Culvert | m3 | 823.48
7 | Rebar Installation | t | 101.656
8 | 洞口帽石 | m3 | 1.86
9 | 涵洞耳墙 | m3 | 47.24
10 | 浆砌块石护底 | m3 | 10.33
11 | Settlement Joint | m | 107.24
（十八） | 5#钢筋砼箱涵4.5*3.0
1 | Excavation | m3 | 1471.55
2 | Gravel Backfill | m3 | 652.09
3 | Excess Disposal (1km) | m3 | 1944.42
4 | Excess Disposal (9km) | m3 | 1944.42
5 | C20 Concrete Base | m3 | 88.683
6 | Rebar Installation | t | 175.01
7 | C30 Box Culvert | m3 | 1174.2
8 | 洞口帽石 | m3 | 1.77
9 | 涵洞耳墙 | m3 | 75.46
10 | 浆砌块石护底 | m3 | 12.45
11 | Settlement Joint | m | 164.2
（十九） | 排水暗沟
1 | Excavation | m3 | 241
2 | Gravel Backfill | m3 | 197.8
3 | Excess Disposal (1km) | m3 | 403
4 | Excess Disposal (9km) | m3 | 403
5 | C25排水暗沟 | m | 510
6 | C10 Concrete Base | m3 | 42.84
（二十） | 管线横穿
1 | Excavation | m3 | 100
2 | Fill | m3 | 100
3 | d500II级钢筋混凝土平口燃气、给水套管 | m | 440
4 | 2*4通信套管 | m | 220
5 | 2*3电力管线套管 | m | 220
（二一） | 地道K26+085.38
1 | Excavation | m3 | 952
2 | Gravel Backfill | m3 | 140
3 | Excess Disposal (1km) | m3 | 952
4 | Excess Disposal (9km) | m3 | 952
5 | C15 Concrete Base | m3 | 41.3
6 | C10 Concrete Base | m3 | 9.3
7 | C10 Concrete Fill | m3 | 161
8 | C20 Concrete帽石 | m3 | 7.87
9 | C20 Concrete排水沟 | m3 | 6.57
10 | C20预制砼盖板 | m3 | 1.68
11 | C30 Concrete悬壁挡墙 | m3 | 100.58
12 | 水泥砂浆抹面 | m2 | 683.9
13 | 侧墙、顶棚乳胶漆 | m2 | 683.9
14 | TS-100透水管 | m | 153
15 | TS-50透水管 | m | 166
16 | 地道侧墙、顶板外防水 | m2 | 924
17 | C30W6防水砼 | m3 | 1019.11
18 | Graded Gravel Filter | m3 | 24.78
19 | Clay Seal Layer | m3 | 21.55
20 | Settlement Joint | m | 69.4
21 | Rebar Installation | t | 172.238
22 | 预制构件钢筋 | t | 0.457
（二二） | 地道K26+398.671
1 | Excavation | m3 | 1034
2 | Gravel Backfill | m3 | 152
3 | Excess Disposal (1km) | m3 | 1034
4 | Excess Disposal (9km) | m3 | 1034
5 | C15 Concrete Base | m3 | 44.84
6 | C10 Concrete Base | m3 | 12.27
7 | C10 Concrete Fill | m3 | 174.8
8 | C20 Concrete帽石 | m3 | 8
9 | C20 Concrete排水沟 | m3 | 7.13
10 | C20预制砼盖板 | m3 | 1.82
11 | C30 Concrete悬壁挡墙 | m3 | 132.66
12 | 水泥砂浆抹面 | m2 | 742.52
13 | 侧墙、顶棚乳胶漆 | m2 | 742.52
14 | TS-100透水管 | m | 164
15 | TS-50透水管 | m | 190.4
16 | 地道侧墙、顶板外防水 | m2 | 1003.2
17 | C30W6防水砼 | m3 | 1106.47
18 | Graded Gravel Filter | m3 | 32.69
19 | Clay Seal Layer | m3 | 28.43
20 | Settlement Joint | m | 104.1
21 | Rebar Installation | t | 189.06
22 | 预制构件钢筋 | t | 0.496
（二三） | 拆除工程
1 | 拆除砼路面 | m2 | 12336
2 | 拆除砼路面每增减1cm | m2 | 12336
3 | 拆除砖石结构 | m3 | 800
4 | 拆除混凝土结构 | m3 | 800
5 | 拆除沥青路面 | m2 | 1210
6 | 拆除人行道 | m2 | 12400
7 | 拆除人行道基层 | m2 | 12400
8 | 拆除人行道基层每增减1cm | m2 | 12400
9 | 拆除沥青路面基层 | m2 | 1210
10 | 拆除沥青路面基层每增减1cm | m2 | 1210
11 | 建渣外运 | m3 | 7789.66
二 | 桥梁工程
董家沟大桥
1 | Excavation | m3 | 5732
2 | Abutment Backfill | m3 | 180
3 | Excess Disposal (1km) | m3 | 12319.68
4 | Excess Disposal (9km) | m3 | 12319.68
5 | Bored Pile D1800 | m | 62.8
6 | Bored Pile D1800 | m | 1297.2
7 | 机械成孔灌注桩Φ1500 | m | 36
8 | 机械成孔灌注桩Φ1500 | m | 36
9 | 机械成孔灌注桩Φ1500 | m | 240
10 | C15混凝土垫层 | m3 | 157.923
11 | C30混凝土承台 | m3 | 2958.65
12 | C40混凝土盖梁 | m3 | 899.66
13 | C30 Concrete Cap | m3 | 140.68
14 | C40 Concrete Column | m3 | 1214.91
15 | C25 Concrete Abutment | m3 | 1303.8
16 | C25 Concrete Foundation | m3 | 499.05
17 | C30枕梁砼 | m3 | 198.4
18 | C30 Precast Slab | m3 | 98.85
19 | C30防水砼 | m2 | 744
20 | AMP-100防水粘性材料 | m2 | 744
21 | Sidewalk Paving | m2 | 868
22 | 人行道栏杆 | m | 620
23 | C30 Crash Barrier | m3 | 56.9
24 | C30预制挂板 | m3 | 60.02
25 | C40钢纤维混凝土 | m3 | 13.9
26 | C40混凝土支座垫石 | m3 | 5.71
27 | C50混凝土铺装层 | m2 | 7440
28 | 纤维增强型防水层 | m2 | 7440
29 | C30 Approach Slab | m3 | 86.4
30 | C20搭板砼垫层 | m3 | 17.2
31 | Cement Stabilized Base 20cm | m2 | 288
32 | Guardrail | m | 300
33 | 桥面伸缩装置SSFB160型 | m | 48
34 | Stone Finish | m2 | 125
35 | 预制非预应力钢筋 圆钢 | t | 11.955
36 | 预制非预应力钢筋 螺纹钢 | t | 8.716
37 | 现浇非预应力钢筋 圆钢 | t | 112.74
38 | 现浇非预应力钢筋 螺纹钢 | t | 1040.032
39 | 预应力钢绞线锚具A15-12 | 套 | 216
40 | 预制砼后张法预应力钢绞线 | t | 29.651
41 | Prestress Conduit D80 | m | 2210.4
普明北路跨线桥
1 | Excavation | m3 | 1890
2 | Abutment Backfill | m3 | 1104.7
3 | Excess Disposal (1km) | m3 | 2162.3
4 | Excess Disposal (9km) | m3 | 2162.3
5 | Bored Pile D1800 | m | 23
6 | Bored Pile D1800 | m | 53
7 | Bored Pile D1800 | m | 104
8 | C15混凝土垫层 | m3 | 80.816
9 | C30混凝土承台 | m3 | 310.5
10 | C40混凝土盖梁 | m3 | 209.5
11 | C30 Concrete Cap | m3 | 66.7
12 | C40 Concrete Column | m3 | 85.09
13 | C25 Concrete Abutment | m3 | 1488.56
14 | C25 Concrete Foundation | m3 | 905.16
15 | C50主梁板砼 | m3 | 2680.6
16 | C30 Crash Barrier | m3 | 53.76
17 | C30预制挂板 | m3 | 19.7
18 | C40钢纤维混凝土 | m3 | 4.9
19 | C40混凝土抗震挡块、垫石、楔块 | m3 | 4.8
20 | C30混凝土防震挡块 | m3 | 60.58
21 | C50混凝土铺装层 | m2 | 3600
22 | 纤维增强型防水层 | m2 | 3600
23 | C30 Approach Slab | m3 | 84.16
24 | C20 Concrete搭板垫层 | m3 | 15.2
25 | Cement Stabilized Base 20cm | m2 | 280.55
26 | Guardrail | m | 640
27 | 盆式橡胶支座 GPZ（II）4.0SX | 个 | 4
28 | 盆式橡胶支座 GPZ（II）4.0DX | 个 | 4
29 | 盆式橡胶支座 GPZ（II）8.0SX | 个 | 2
30 | 盆式橡胶支座 GPZ（II）8.0DX | 个 | 2
31 | 盆式橡胶支座 GPZ（II）9.0DX | 个 | 4
32 | 盆式橡胶支座 GPZ（II）9.0SX | 个 | 2
33 | 盆式橡胶支座 GPZ（II）9.0GX | 个 | 2
34 | 桥面伸缩装置80型 | m | 48
35 | PVC泄水管 φ150 | m | 455.7
36 | Graded Gravel Filter | m3 | 186.29
37 | Clay Seal Layer | m3 | 11.5
38 | Φ50PVC排水管 | m | 90
39 | 碎石盲沟 | m | 20
40 | Stone Finish | m2 | 423.2
41 | 预制非预应力钢筋 圆钢 | t | 3.686
42 | 现浇非预应力钢筋 圆钢 | t | 32.81
43 | 现浇非预应力钢筋 螺纹钢 | t | 767.224
44 | 预应力钢绞线锚具A15-19 | 套 | 72
45 | 预制砼后张法预应力钢绞线 | t | 106.516
46 | Prestress Conduit D100 | m | 5034.2
K25+640跨线桥
1 | Excavation | m3 | 636
2 | Abutment Backfill | m3 | 302.96
3 | Excess Disposal (1km) | m3 | 926
4 | Excess Disposal (9km) | m3 | 926
5 | 人工挖孔桩Φ1800 | m | 20
6 | C30枕梁砼 | m3 | 14.24
7 | C30防水砼 | m2 | 120
8 | C30 Precast Slab | m3 | 9.03
9 | AMP-100防水粘性材料 | m2 | 111.6
10 | C40 Concrete Column | m3 | 14.72
11 | Sidewalk Paving | m2 | 117
12 | 人行道栏杆 | m | 50.000
13 | C30 Concrete Cap | m3 | 25.200
14 | C25 Concrete Abutment | m3 | 612.480
15 | C25 Concrete Foundation | m3 | 368.220
16 | C15 Concrete Base | m3 | 21.250
17 | C40主梁板砼 | m3 | 275.410
18 | C30 Crash Barrier | m3 | 19.220
19 | C30预制挂板 | m3 | 8.100
20 | C50钢纤维混凝土 | m3 | 1.580
21 | C40混凝土垫石、楔块 | m3 | 0.550
22 | C30混凝土防震挡块 | m3 | 11.420
23 | C50混凝土铺装层 | m2 | 280.000
24 | 纤维增强型防水层 | m2 | 280.000
25 | C30 Approach Slab | m3 | 25.200
26 | C20搭板砼垫层 | m3 | 5.040
27 | Cement Stabilized Base 20cm | m2 | 84.000
28 | Guardrail | m | 100.000
29 | 盆式橡胶支座 GPZ（II）3.0SX | 个 | 2.000
30 | 盆式橡胶支座 GPZ（II）3.0DX | 个 | 2.000
31 | 盆式橡胶支座 GPZ（II）5.0DX | 个 | 1.000
32 | 盆式橡胶支座 GPZ（II）5.0GX | 个 | 1.000
33 | 桥面伸缩装置40型 | m | 20.000
34 | PVC泄水管 φ120 | m | 43.000
35 | Graded Gravel Filter | m3 | 79.56
36 | Clay Seal Layer | m3 | 2.34
37 | Φ50PVC排水管 | m | 12
38 | 碎石盲沟 | m | 6.88
39 | Stone Finish | m2 | 207.48
40 | 预制非预应力钢筋 圆钢 | t | 2.892
41 | 现浇非预应力钢筋 圆钢 | t | 3.906
42 | 现浇非预应力钢筋 螺纹钢 | t | 95.181
洛阳路桥建设集团Company绵阳市二环路十五Contract段Project部 工程部制

## Sheet1
ConstructionProgress横道图
序 号 | 工程Project Name | Quantity |  | ContractDuration450天，ProgressPlanned若受拆迁等因素影响，Duration相应顺延。
|  |  |  | 2010Year | [15 empty] | 2011Year | [47 empty] | 2012Year | [7 empty] | Notes
|  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | 3Month份 |  |  |  | 4Month份 |  |  |  | 5Month份 |  |  |  | 6Month份 |  |  |  | 7Month份 |  |  |  | 8Month份 |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February
|  | Unit | Quantity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72
一 | 道排工程
路基土石方工程
1 | 清除表土 | m3 | 46897
2 | 清除淤泥、流沙 | m3 | 3486
3 | Road Excavation | m3 | 239438
4 | 挖Normal道路石方 | m3 | 200163
5 | 土石方方回填 | m3 | 363497
6 | 道路回填砂砾石 | m3 | 9580
路面结构工程（K24+000-K27+212.294）
1 | 路床整形碾压 | m2 | 102303
2 | Shoulder Rolling | m2 | 12756.42
3 | 主车道路路缘石、平石等 | m | 18937
4 | Medium央分隔带、侧分带种植土回填 | m3 | 8180.25
5 | Medium央分隔带、侧分带防渗土工布 | m2 | 9896.24
6 | Medium央分隔带、侧分带碎石盲沟 | m | 3772
7 | 填挖交界处碎石盲沟 | m | 350
8 | C20 Permeable Base | m2 | 4598
9 | Gravel Base Course | m2 | 4598
10 | Sidewalk Paving | m2 | 4598
11 | C15混凝土基座 | m3 | 43
12 | 防撞护栏C30混凝土基础 | m3 | 218.24
13 | 土工格栅 | m2 | 5660
14 | 防撞护栏 | m | 760.4
道路改造工程（K27+212.294-K28+737.937）
1 | Road Excavation | m3 | 4800
2 | 利用Earth Backfill | m3 | 1210
3 | Shoulder Rolling | m2 | 12400
4 | C20 Permeable Base | m2 | 12400
5 | Gravel Base Course | m2 | 12400
6 | Sidewalk Paving | m2 | 12400
7 | Medium央分隔带路缘石、嵌边石等 | m | 6405
重力式挡墙
1 | Trench Excavation | m3 | 2827.2
2 | Trench Backfill | m3 | 1403
3 | 回填砂卵石 | m3 | 843.6
4 | 回填块石或卵石 | m3 | 433.2
5 | C20片石砼墙身 | m3 | 190
6 | Graded Gravel Filter | m3 | 34.2
7 | Clay Seal Layer、隔水层 | m3 | 68.4
悬臂式挡墙
1 | Trench Excavation | m3 | 13445
2 | Trench Backfill | m3 | 5901
3 | Foundation Sand Backfill | m3 | 4442.66
4 | Foundation Rock Backfill | m3 | 2094.72
5 | C10 Concrete Base | m3 | 227.16
6 | C30现浇钢筋混凝土墙身 | m3 | 1848
7 | Graded Gravel Filter | m3 | 428
8 | Clay Seal Layer | m3 | 1513.58
（六） | 扶壁式挡墙
1 | Trench Excavation | m3 | 1684.62
2 | Trench Backfill | m3 | 600
3 | Foundation Sand Backfill | m3 | 586.2
4 | Foundation Rock Backfill | m3 | 270.6
5 | C10 Concrete Base | m3 | 33.22
6 | C30现浇钢筋混凝土墙身 | m3 | 497.25
7 | Graded Gravel Filter | m3 | 107
8 | Clay Seal Layer | m3 | 15.6
（七） | 植被混凝土护坡
1 | 平台喷射混凝土封面 | m3 | 880
2 | Φ14锚杆支护 | m | 33726
（八） | 网格护坡
1 | M7.5 Mortar Rubble | m3 | 189.8
（九） | 截水沟
1 | Trench Excavation & Haul | m3 | 1075.7
2 | M7.5 Mortar Rubble | m3 | 733.3
（十） | 排水沟
1 | Trench Excavation & Haul | m3 | 3788.5
2 | M7.5 Mortar Rubble | m3 | 2768.5
（十一） | 浅碟形边沟
1 | Trench Excavation & Haul | m3 | 1892
2 | M7.5 Mortar Rubble | m3 | 1248.72
3 | 碎石盲沟 | m | 1720
4 | 预制混凝土盖板 | m3 | 149.64
5 | 防渗土工布 | m2 | 5607.2
6 | 黑色三维网 | m2 | 7585.2
7 | 种植土回填 | m3 | 2167.2
（十二） | LB-M52型生态护坡
1 | 0.4mm厚阻水膜 | m2 | 2544.6
2 | C20混凝土基础 | m3 | 856.38
（十三） | 排水工程
1 | Trench Excavation | m3 | 8184.4
2 | Trench Backfill | m3 | 3494.33
3 | 沟槽回填砂卵石 | m3 | 5863.26
4 | 井周回填水稳碎石 | m3 | 1898.17
5 | 管道铺设 | m | 4300
6 | 污水混凝土检查井 | 座 | 30
7 | 雨水混凝土检查井 | 座 | 114
8 | 雨水双蓖井 | 座 | 104
（十四） | 3#矩形明沟2.0*1.5
1 | Excavation | m3 | 389.664
2 | Fill | m3 | 155.36
3 | M10 Mortar MU30 Rubble | m3 | 234.3
（十五） | 2#、4#矩形明沟5.0*2.0
1 | Excavation | m3 | 3051.5
2 | Fill | m3 | 1826.6
3 | M10 Mortar MU30 Rubble | m3 | 1226.88
（十六） | 3#钢筋砼箱涵5.0*3.0
1 | Excavation | m3 | 2469.26
2 | C20 Concrete Base | m3 | 81
3 | C30 Box Culvert | m3 | 745.2
4 | Rebar Installation | t | 153.862
5 | 进出口八字墙 | m3 | 90
（十七） | 4#双孔钢筋砼箱涵2*2.5*2.0
1 | Excavation | m3 | 754.94
2 | Gravel Backfill | m3 | 211.63
3 | C20 Concrete Base | m3 | 62.22
4 | C30 Box Culvert | m3 | 823.48
5 | Rebar Installation | t | 101.656
6 | 进出口八字墙 | m3 | 60
（十八） | 5#钢筋砼箱涵4.5*3.0
1 | Excavation | m3 | 1471.55
2 | Gravel Backfill | m3 | 652.09
3 | C20 Concrete Base | m3 | 88.683
4 | Rebar Installation | t | 175.01
5 | C30 Box Culvert | m3 | 1174.2
6 | 进出口八字墙 | m3 | 90
（十九） | 排水暗沟
1 | Excavation | m3 | 241
2 | Gravel Backfill | m3 | 197.8
3 | C25排水暗沟 | m | 510
4 | C10 Concrete Base | m3 | 42.84
（二十） | 管线横穿
1 | Excavation | m3 | 100
2 | Fill | m3 | 100
3 | 管线敷设 | m | 880
（二一） | 地道K26+085.38
1 | Excavation | m3 | 952
2 | Gravel Backfill | m3 | 140
3 | C15 Concrete Base | m3 | 41.3
4 | C10 Concrete Base | m3 | 9.3
5 | 钢筋 | t | 172.695
6 | C30W6防水砼 | m3 | 7.87
7 | C20 Concrete排水沟 | m3 | 6.57
8 | C30 Concrete悬壁挡墙 | m3 | 100.58
9 | 水泥砂浆抹面 | m2 | 683.9
10 | 侧墙、顶棚乳胶漆 | m2 | 683.9
11 | 地道侧墙、顶板外防水 | m2 | 924
12 | C10 Concrete Fill | m3 | 1019.11
13 | Graded Gravel Filter | m3 | 24.78
14 | Clay Seal Layer | m3 | 21.55
15 | C20 Concrete帽石 | t | 172.695
（二二） | 地道K26+398.671
1 | Excavation | m3 | 1034
2 | Gravel Backfill | m3 | 152
3 | C15 Concrete Base | m3 | 44.84
4 | C10 Concrete Base | m3 | 12.27
5 | C30W6防水钢筋砼 | m3 | 1106.47
6 | C20 Concrete排水沟 | m3 | 7.13
7 | C30 Concrete悬壁挡墙 | m3 | 132.66
8 | 水泥砂浆抹面 | m2 | 742.52
9 | 侧墙、顶棚乳胶漆 | m2 | 742.52
10 | 地道侧墙、顶板外防水 | m2 | 1003.2
11 | Graded Gravel Filter | m3 | 32.69
12 | Clay Seal Layer | m3 | 28.43
13 | C10 Concrete Fill | m3 | 174.8
14 | C20 Concrete帽石 | m3 | 8
（二三） | 拆除工程
1 | 拆除砼路面 | m2 | 12336
2 | 拆除砼路面每增减1cm | m2 | 12336
3 | 拆除砖石结构 | m3 | 800
4 | 拆除混凝土结构 | m3 | 800
5 | 拆除沥青路面 | m2 | 1210
6 | 拆除人行道 | m2 | 12400
7 | 拆除人行道基层 | m2 | 12400
8 | 拆除人行道基层每增减1cm | m2 | 12400
9 | 拆除沥青路面基层 | m2 | 1210
10 | 拆除沥青路面基层每增减1cm | m2 | 1210
二 | 桥梁工程
董家沟大桥
1 | Excavation | m3 | 5732
2 | Abutment Backfill | m3 | 180
3 | Bored Pile D1800 | m | 1360
4 | 机械成孔灌注桩Φ1500 | m | 312
5 | C15混凝土垫层 | m3 | 157.923
6 | C30混凝土承台 | m3 | 2958.65
7 | C40混凝土盖梁 | m3 | 899.66
8 | C30 Concrete Cap | m3 | 140.68
9 | C40 Concrete Column | m3 | 1214.91
10 | C25 Concrete Abutment | m3 | 1303.8
11 | C25 Concrete Foundation | m3 | 499.05
12 | C30枕梁砼 | m3 | 198.4
13 | C30 Precast Slab | m3 | 98.85
14 | C30防水砼 | m2 | 7440
15 | Sidewalk Paving | m2 | 868
16 | 人行道栏杆 | m | 620
17 | C30 Crash Barrier | m3 | 56.9
18 | C40混凝土支座垫石 | m3 | 5.71
19 | 铺装层 | m2 | 7440
20 | C30 Approach Slab | m3 | 86.4
21 | C20搭板砼垫层 | m3 | 17.2
22 | Cement Stabilized Base 20cm | m2 | 288
23 | Guardrail | m | 300
24 | 桥面伸缩装置SSFB160型 | m | 48
25 | Stone Finish | m2 | 125
26 | 钢筋 | t | 1172.67
27 | 预应力钢绞线锚具A15-12 | 套 | 216
28 | 预制砼后张法预应力钢绞线 | t | 29.651
普明北路跨线桥
1 | Excavation | m3 | 1890
2 | Abutment Backfill | m3 | 1104.7
3 | Bored Pile D1800 | m | 180
4 | C15混凝土垫层 | m3 | 80.816
5 | C30钢筋混凝土承台 | m3 | 310.5
6 | C40钢筋混凝土盖梁 | m3 | 209.5
7 | C30钢筋混凝土台帽 | m3 | 66.7
8 | C40钢筋混凝土墩柱 | m3 | 85.09
9 | C25 Concrete Abutment | m3 | 1488.56
10 | C25 Concrete Foundation | m3 | 905.16
11 | C50主梁板钢筋砼 | m3 | 2680.6
12 | C30 Crash Barrier | m3 | 53.76
14 | C40混凝土抗震挡块、垫石、楔块 | m3 | 4.8
15 | 铺装层 | m2 | 3600
16 | C30 Approach Slab | m3 | 84.16
17 | C20 Concrete搭板垫层 | m3 | 15.2
18 | Cement Stabilized Base 20cm | m2 | 280.55
19 | Guardrail | m | 640
20 | 盆式橡胶支座 | 个 | 20
21 | 桥面伸缩装置80型 | m | 48
22 | Stone Finish | m2 | 423.2
24 | 预制砼后张法预应力钢绞线 | t | 106.516
K25+640跨线桥
1 | Excavation | m3 | 636
2 | Abutment Backfill | m3 | 302.96
3 | 人工挖孔桩Φ1800 | m | 20
6 | C30 Precast Slab | m3 | 9.03
7 | C40 Concrete Column | m3 | 14.72
8 | Sidewalk Paving | m2 | 117
9 | 人行道栏杆 | m | 50
10 | C30 Concrete Cap | m3 | 25.2
11 | C25 Concrete Abutment | m3 | 612.48
12 | C25 Concrete Foundation | m3 | 368.22
13 | C15 Concrete Base | m3 | 21.25
14 | C40主梁板砼 | m3 | 275.41
15 | C30 Crash Barrier | m3 | 19.22
16 | C50钢纤维混凝土 | m3 | 1.58
17 | C40混凝土垫石、楔块 | m3 | 0.55
18 | C30混凝土防震挡块 | m3 | 11.42
19 | 铺装层 | m2 | 280
20 | C30 Approach Slab | m3 | 25.2
21 | C20搭板砼垫层 | m3 | 5.04
22 | Cement Stabilized Base 20cm | m2 | 84
23 | Guardrail | m | 100
24 | 盆式橡胶支座 | 个 | 6 | October 5: C30 Precast Slab; October 6: m3; October 7: 9.03
25 | 桥面伸缩装置40型 | m | 20
26 | Graded Gravel Filter | m3 | 79.56
27 | Stone Finish | m2 | 207.48
洛阳路桥建设集团Company绵阳市二环路十五Contract段Project部 工程部制

## Sheet2
绵阳市二环路十五Contract段ConstructionProgress横道图
序 号 | 工程Project Name | Quantity |  | ContractDuration450天，ProgressPlanned若受拆迁等因素影响，Duration相应顺延。
|  |  |  | 2010Year | [15 empty] | 2011Year | [47 empty] | 2012Year | [7 empty] | Notes
|  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | 3Month份 |  |  |  | 4Month份 |  |  |  | 5Month份 |  |  |  | 6Month份 |  |  |  | 7Month份 |  |  |  | 8Month份 |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February
|  | Unit | Quantity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72
一 | 道排工程
路基土石方工程
1 | 清除表土 | m3 | 46897
2 | 清除淤泥、流沙 | m3 | 3486
3 | Road Excavation | m3 | 239438
4 | 挖Normal道路石方 | m3 | 200163
5 | 土石方方回填 | m3 | 363497
6 | 道路回填砂砾石 | m3 | 9580
路面结构工程（K24+000-K27+212.294）
1 | 路床整形碾压 | m2 | 102303
2 | Shoulder Rolling | m2 | 12756.42
3 | 主车道路路缘石、平石等 | m | 18937
4 | Medium央分隔带、侧分带种植土回填 | m3 | 8180.25
5 | Medium央分隔带、侧分带防渗土工布 | m2 | 9896.24
6 | Medium央分隔带、侧分带碎石盲沟 | m | 3772
7 | 填挖交界处碎石盲沟 | m | 350
8 | Sidewalk Paving | m2 | 4598
9 | C20 Permeable Base | m2 | 4598
10 | Gravel Base Course | m2 | 4598
11 | C15混凝土基座 | m3 | 43
12 | 防撞护栏C30混凝土基础 | m3 | 218.24
13 | 土工格栅 | m2 | 5660
14 | 防撞护栏 | m | 760.4
15 | Rebar Installation | t | 40.58
道路改造工程（K27+212.294-K28+737.937）
1 | Road Excavation | m3 | 4800
2 | 利用Earth Backfill | m3 | 1210
3 | Shoulder Rolling | m2 | 12400
4 | Sidewalk Paving | m2 | 12400
5 | C20 Permeable Base | m2 | 12400
6 | Gravel Base Course | m2 | 12400
7 | Medium央分隔带路缘石、嵌边石等 | m | 6405
重力式挡墙
1 | Trench Excavation | m3 | 2827.2
2 | Trench Backfill | m3 | 1403
3 | 回填砂卵石 | m3 | 843.6
4 | 回填块石或卵石 | m3 | 433.2
5 | C20片石砼墙身 | m3 | 190
6 | Graded Gravel Filter | m3 | 34.2
7 | Clay Seal Layer、隔水层 | m3 | 68.4
悬臂式挡墙
1 | Trench Excavation | m3 | 13445
2 | Trench Backfill | m3 | 5901
3 | Foundation Sand Backfill | m3 | 4442.66
4 | Foundation Rock Backfill | m3 | 2094.72
5 | C10 Concrete Base | m3 | 227.16
6 | C30现Concrete Pour墙身 | m3 | 1848
7 | Graded Gravel Filter | m3 | 428
8 | Clay Seal Layer | m3 | 1513.58
9 | Rebar Installation | t | 174.48
（六） | 扶壁式挡墙
1 | Trench Excavation | m3 | 1684.62
2 | Trench Backfill | m3 | 600
3 | Foundation Sand Backfill | m3 | 586.2
4 | Foundation Rock Backfill | m3 | 270.6
5 | C10 Concrete Base | m3 | 33.22
6 | C30现Concrete Pour墙身 | m3 | 497.25
7 | Graded Gravel Filter | m3 | 107
8 | Clay Seal Layer | m3 | 15.6
9 | Rebar Installation | t | 46.57
（七） | 植被混凝土护坡
1 | 平台喷射混凝土封面 | m3 | 880
2 | Φ14锚杆支护 | m | 33726
（八） | 网格护坡
1 | M7.5 Mortar Rubble | m3 | 189.8
（九） | 截水沟
1 | Trench Excavation & Haul | m3 | 1075.7
2 | M7.5 Mortar Rubble | m3 | 733.3
（十） | 排水沟
1 | Trench Excavation & Haul | m3 | 3788.5
2 | M7.5 Mortar Rubble | m3 | 2768.5
（十一） | 浅碟形边沟
1 | Trench Excavation & Haul | m3 | 1892
2 | M7.5 Mortar Rubble | m3 | 1248.72
3 | 碎石盲沟 | m | 1720
4 | 预制混凝土盖板 | m3 | 149.64
5 | 防渗土工布 | m2 | 5607.2
6 | 黑色三维网 | m2 | 7585.2
7 | 种植土回填 | m3 | 2167.2
（十二） | LB-M52型生态护坡
1 | 0.4mm厚阻水膜 | m2 | 2544.6
2 | C20混凝土基础 | m3 | 856.38
（十三） | 排水工程
1 | Trench Excavation | m3 | 8184.4
2 | Trench Backfill | m3 | 3494.33
3 | 沟槽回填砂卵石 | m3 | 5863.26
4 | 井周回填水稳碎石 | m3 | 1898.17
5 | 管道铺设 | m | 4300
6 | 污水混凝土检查井 | 座 | 30
7 | 雨水混凝土检查井 | 座 | 114
8 | 雨水双蓖井 | 座 | 104
（十四） | 3#矩形明沟2.0*1.5
1 | Excavation | m3 | 389.664
2 | Fill | m3 | 155.36
3 | M10 Mortar MU30 Rubble | m3 | 234.3
（十五） | 2#、4#矩形明沟5.0*2.0
1 | Excavation | m3 | 3051.5
2 | Fill | m3 | 1826.6
3 | M10 Mortar MU30 Rubble | m3 | 1226.88
（十六） | 3#钢筋砼箱涵5.0*3.0
1 | Excavation | m3 | 2469.26
2 | C20 Concrete Base | m3 | 81
3 | C30 Box Culvert | m3 | 745.2
4 | Rebar Installation | t | 153.862
5 | 进出口八字墙 | m3 | 90
（十七） | 4#双孔钢筋砼箱涵2*2.5*2.0
1 | Excavation | m3 | 754.94
2 | Gravel Backfill | m3 | 211.63
3 | C20 Concrete Base | m3 | 62.22
4 | C30 Box Culvert | m3 | 823.48
5 | Rebar Installation | t | 101.656
6 | 进出口八字墙 | m3 | 60
（十八） | 5#钢筋砼箱涵4.5*3.0
1 | Excavation | m3 | 1471.55
2 | Gravel Backfill | m3 | 652.09
3 | C20 Concrete Base | m3 | 88.683
4 | Rebar Installation | t | 175.01
5 | C30 Box Culvert | m3 | 1174.2
6 | 进出口八字墙 | m3 | 90
（十九） | 排水暗沟
1 | Excavation | m3 | 241
2 | Gravel Backfill | m3 | 197.8
3 | C25排水暗沟 | m | 510
4 | C10 Concrete Base | m3 | 42.84
（二十） | 管线横穿
1 | Excavation | m3 | 100
2 | Fill | m3 | 100
3 | 管线敷设 | m | 880
（二一） | 地道K26+085.38
1 | Excavation | m3 | 952
2 | Gravel Backfill | m3 | 140
3 | C15 Concrete Base | m3 | 41.3
4 | C10 Concrete Base | m3 | 9.3
5 | C10 Concrete Fill | m3 | 161
6 | C20 Concrete帽石 | m3 | 7.87
7 | C20 Concrete排水沟 | m3 | 6.57
8 | C30 Concrete悬壁挡墙 | m3 | 100.58
9 | 水泥砂浆抹面 | m2 | 683.9
10 | 侧墙、顶棚乳胶漆 | m2 | 683.9
11 | 地道侧墙、顶板外防水 | m2 | 924
12 | C30W6防水砼 | m3 | 1019.11
13 | Graded Gravel Filter | m3 | 24.78
14 | Clay Seal Layer | m3 | 21.55
15 | 钢筋 | t | 172.695
（二二） | 地道K26+398.671
1 | Excavation | m3 | 1034
2 | Gravel Backfill | m3 | 152
3 | C15 Concrete Base | m3 | 44.84
4 | C10 Concrete Base | m3 | 12.27
5 | C10 Concrete Fill | m3 | 174.8
6 | C20 Concrete帽石 | m3 | 8
7 | C20 Concrete排水沟 | m3 | 7.13
8 | C30 Concrete悬壁挡墙 | m3 | 132.66
9 | 水泥砂浆抹面 | m2 | 742.52
10 | 侧墙、顶棚乳胶漆 | m2 | 742.52
11 | 地道侧墙、顶板外防水 | m2 | 1003.2
12 | C30W6防水砼 | m3 | 1106.47
13 | Graded Gravel Filter | m3 | 32.69
14 | Clay Seal Layer | m3 | 28.43
15 | 钢筋 | t | 189.556
（二三） | 拆除工程
1 | 拆除砼路面 | m2 | 12336
2 | 拆除砼路面每增减1cm | m2 | 12336
3 | 拆除砖石结构 | m3 | 800
4 | 拆除混凝土结构 | m3 | 800
5 | 拆除沥青路面 | m2 | 1210
6 | 拆除人行道 | m2 | 12400
7 | 拆除人行道基层 | m2 | 12400
8 | 拆除人行道基层每增减1cm | m2 | 12400
9 | 拆除沥青路面基层 | m2 | 1210
10 | 拆除沥青路面基层每增减1cm | m2 | 1210
二 | 桥梁工程
董家沟大桥
1 | Excavation | m3 | 5732
2 | Abutment Backfill | m3 | 180
3 | Bored Pile D1800 | m | 1360
4 | 机械成孔灌注桩Φ1500 | m | 312
5 | C15混凝土垫层 | m3 | 157.923
6 | C30混凝土承台 | m3 | 2958.65
7 | C40混凝土盖梁 | m3 | 899.66
8 | C30 Concrete Cap | m3 | 140.68
9 | C40 Concrete Column | m3 | 1214.91
10 | C25 Concrete Abutment | m3 | 1303.8
11 | C25 Concrete Foundation | m3 | 499.05
12 | C30枕梁砼 | m3 | 198.4
13 | C30 Precast Slab | m3 | 98.85
14 | C30防水砼 | m2 | 7440
15 | Sidewalk Paving | m2 | 868
16 | 人行道栏杆 | m | 620
17 | C30 Crash Barrier | m3 | 56.9
18 | C40混凝土支座垫石 | m3 | 5.71
19 | 铺装层 | m2 | 7440
20 | C30 Approach Slab | m3 | 86.4
21 | C20搭板砼垫层 | m3 | 17.2
22 | Cement Stabilized Base 20cm | m2 | 288
23 | Guardrail | m | 300
24 | 桥面伸缩装置SSFB160型 | m | 48
25 | Stone Finish | m2 | 125
26 | 钢筋 | t | 1172.67
27 | 预应力钢绞线锚具A15-12 | 套 | 216
28 | 预制砼后张法预应力钢绞线 | t | 29.651
普明北路跨线桥
1 | Excavation | m3 | 1890
2 | Abutment Backfill | m3 | 1104.7
3 | Bored Pile D1800 | m | 180
4 | C15混凝土垫层 | m3 | 80.816
5 | C30混凝土承台 | m3 | 310.5
6 | C40混凝土盖梁 | m3 | 209.5
7 | C30 Concrete Cap | m3 | 66.7
8 | C40 Concrete Column | m3 | 85.09
9 | C25 Concrete Abutment | m3 | 1488.56
10 | C25 Concrete Foundation | m3 | 905.16
11 | C50主梁板砼 | m3 | 2680.6
12 | C30 Crash Barrier | m3 | 53.76
13 | C40钢纤维混凝土 | m3 | 4.9
14 | C40混凝土抗震挡块、垫石、楔块 | m3 | 4.8
15 | 铺装层 | m2 | 3600
16 | C30 Approach Slab | m3 | 84.16
17 | C20 Concrete搭板垫层 | m3 | 15.2
18 | Cement Stabilized Base 20cm | m2 | 280.55
19 | Guardrail | m | 640
20 | 盆式橡胶支座 | 个 | 20
21 | 桥面伸缩装置80型 | m | 48
22 | Stone Finish | m2 | 423.2
23 | 预制非预应力钢筋 圆钢 | t | 803.72
24 | 预制砼后张法预应力钢绞线 | t | 106.516
K25+640跨线桥
1 | Excavation | m3 | 636
2 | Abutment Backfill | m3 | 302.96
3 | 人工挖孔桩Φ1800 | m | 20
4 | C30枕梁砼 | m3 | 14.24
5 | C30防水砼 | m2 | 120
6 | C30 Precast Slab | m3 | 9.03
7 | C40 Concrete Column | m3 | 14.72
8 | Sidewalk Paving | m2 | 117
9 | 人行道栏杆 | m | 50
10 | C30 Concrete Cap | m3 | 25.2
11 | C25 Concrete Abutment | m3 | 612.48
12 | C25 Concrete Foundation | m3 | 368.22
13 | C15 Concrete Base | m3 | 21.25
14 | C40主梁板砼 | m3 | 275.41
15 | C30 Crash Barrier | m3 | 19.22
16 | C50钢纤维混凝土 | m3 | 1.58
17 | C40混凝土垫石、楔块 | m3 | 0.55
18 | C30混凝土防震挡块 | m3 | 11.42
19 | 铺装层 | m2 | 280
20 | C30 Approach Slab | m3 | 25.2
21 | C20搭板砼垫层 | m3 | 5.04
22 | Cement Stabilized Base 20cm | m2 | 84
23 | Guardrail | m | 100
24 | 盆式橡胶支座 | 个 | 6
25 | 桥面伸缩装置40型 | m | 20
26 | Graded Gravel Filter | m3 | 79.56
27 | Stone Finish | m2 | 207.48
28 | 钢筋 | t | 101.98
洛阳路桥建设集团Company绵阳市二环路十五Contract段Project部 工程部制