## Sheet1
Task列表 | 执行部门 | 执行人 | Planned Start | Duration | PlanEnd Time | AdjustmentPlanned Start | AdjustmentPlanEnd Time | AdjustmentDuration | ActualStart Time | ActualEnd Time | Duration | 延迟开始Days | 延迟DoneDays | 原因
Initiation |  |  | 2013-02-20 | 3 | 2013-02-23 | 2013-02-21 | 2013-02-22 | 1 | 2013-02-21 | 2013-02-22 | 1 | 1 | -1
Collect Supplier Info |  |  | 2013-02-24 | 3 | 2013-02-27 | 2013-02-23 | 2013-03-01 | 6 | 2013-02-23 | 2013-03-01 | 6 | -1 | 2
Verify Supplier Info |  |  | 2013-02-28 | 1 | 2013-03-01 | 2013-03-01 | 2013-03-02 | 1 | 2013-03-01 | 2013-03-02 | 1 | 1 | 1
Supplier Audit |  |  | 2013-03-01 | 2 | 2013-03-03 | 2013-03-03 | 2013-03-04 | 1 | 2013-03-03 | 2013-03-04 | 1 | 2 | 1
Submit Supplier Audit Report |  |  | 2013-03-04 | 5 | 2013-03-09 | 2013-03-05 | 2013-03-08 | 3 | 2013-03-05 | 2013-03-08 | 3 | 1 | -1
Shortlist Supplier Confirmed |  |  | 2013-03-10 | 2 | 2013-03-12 | 2013-03-09 | 2013-03-12 | 3 | 2013-03-09 | 2013-03-12 | 3 | -1 | 0
各部门提交招标文件资料 |  |  | 2013-03-13 | 10 | 2013-03-23 | 2013-03-13 | 2013-03-23 | 10 | 2013-03-13 | 2013-03-23 | 10 | 0 | 0
Tender Documents |  |  | 2013-03-23 | 1 | 2013-03-24 | 2013-03-24 | 2013-03-25 | 1 | 2013-03-24 |  | 2 | 1 | 0
Issue Tender |  |  | 2013-03-25 | 5 | 2013-03-30 | 2013-03-26 | 2013-03-31 | 5 |  |  |  | 0 | 0
Clarifications |  |  | 2013-03-31 | 5 | 2013-04-05 | 2013-04-01 | 2013-04-06 | 5 |  |  |  | 0 | 0
Bid Opening |  |  | 2013-04-06 | 1 | 2013-04-07 | 2013-04-07 | 2013-04-08 | 1 |  |  |  | 0 | 0
Contract Negotiation |  |  | 2013-04-08 | 10 | 2013-04-18 | 2013-04-09 | 2013-04-19 | 10 |  |  |  | 0 | 0
Contract Signing |  |  | 2013-04-18 | 3 | 2013-04-21 | 2013-04-19 | 2013-04-22 | 3 |  |  |  | 0 | 0
[5 empty] | 41325 | 41426 | 41326
|  | Plan | Plan Duration | Actual | Actual Duration | AdjustmentStart Time | AdjustmentDuration
| Initiation | 2013-02-20 | 3 | 2013-02-21 | 1
[6 empty] | 2013-02-21 | 1
| Collect Supplier Info | 2013-02-24 | 3 | 2013-02-23 | 6
[6 empty] | 2013-02-23 | 6
| Verify Supplier Info | 2013-02-28 | 1 | 2013-03-01 | 1
[6 empty] | 2013-03-01 | 1
| Supplier Audit | 2013-03-01 | 2 | 2013-03-03 | 1
[6 empty] | 2013-03-03 | 1
| Submit Supplier Audit Report | 2013-03-04 | 5 | 2013-03-05 | 3
[6 empty] | 2013-03-05 | 3
| Shortlist Supplier Confirmed | 2013-03-10 | 2 | 2013-03-09 | 3
[6 empty] | 2013-03-09 | 3
| 各部门提交招标文件资料 | 2013-03-13 | 10 | 2013-03-13 | 10
[6 empty] | 2013-03-13 | 10
| Tender Documents | 2013-03-23 | 1 | 2013-03-24 | 2
[6 empty] | 2013-03-24 | 1
| Issue Tender | 2013-03-25 | 5 | 0
[6 empty] | 2013-03-26 | 5
| Clarifications | 2013-03-31 | 5 | 0
[6 empty] | 2013-04-01 | 5
| Bid Opening | 2013-04-06 | 1 | 0
[6 empty] | 2013-04-07 | 1
| Contract Negotiation | 2013-04-08 | 10 | 0
[6 empty] | 2013-04-09 | 10
| Contract Signing | 2013-04-18 | 3 | 0
[6 empty] | 2013-04-19 | 3
Formulas:
PlanEnd Time = [Planned Start]+[Duration]
AdjustmentPlanned Start = IF([ActualStart Time]="",[Planned Start],[ActualStart Time])
AdjustmentPlanned Start = IF([ActualStart Time]="",[AdjustmentPlanEnd Time, row above]+([Planned Start]-[PlanEnd Time, row above]),[ActualStart Time])
AdjustmentPlanEnd Time = IF([ActualEnd Time]="",[AdjustmentPlanned Start]+[Duration],[ActualEnd Time])
Duration = IF([ActualStart Time]="","",IF([ActualEnd Time]<>"",[ActualEnd Time]-[ActualStart Time],TODAY()-[ActualStart Time]))