## Work Plan Progress
Work Plan Progress |  |  |  |  | Not Started | 2 | In Progress | 3 | Completed | 3
No. | Task Name | Task具体内容 | Owner | Planned Start | Planned End | TaskStatus | TaskDays | CompletedDays | Remaining Days | Progress
1 | 绘制图纸 | ProjectConstruction | 王小明 | 2021-04-10 | 2021-04-17 | Completed | 7 | 7 | 0 | 100%
2 | ProjectBudget |  |  | 2021-03-01 | 2021-04-28 | Completed | 58 | 58 | 0 | 100%
3 | ConstructionProgress |  |  | 2021-01-05 | 2021-09-13 | In Progress | 251 | 180 | 71 | 71.71%
4 | 外表装饰 |  |  | 2021-02-25 | 2021-03-05 | Completed | 8 | 8 | 0 | 100%
5 | 铺地刮白 |  |  | 2021-02-08 | 2021-09-30 | In Progress | 234 | 146 | 88 | 62.39%
6 | 购买家具 |  |  | 2020-09-03 | 2021-10-10 | In Progress | 402 | 304 | 98 | 75.62%
7 | 整体装修 |  |  | 2021-10-10 | 2021-11-30 | Not Started | 51 | 0 | 51 | 0%
8 | 后期Acceptance |  |  | 2021-12-02 | 2021-12-26 | Not Started | 24 | 0 | 24 | 0%
Formulas:
TaskStatus = IF(OR([Planned Start]="",[Planned End]=""),"",IF(TODAY()<[Planned Start],"Not Started",IF(TODAY()>[Planned End],"Completed","In Progress")))
CompletedDays = IF([Planned Start]="","",IF(TODAY()-[Planned Start]<=0,0,IF(TODAY()-[Planned Start]<=[TaskDays],TODAY()-[Planned Start],[TaskDays])))
Remaining Days = IF(OR([Planned Start]="",[Planned End]=""),"",IF(TODAY()-[Planned Start]<=0,[TaskDays],IF(TODAY()-[Planned Start]<=[TaskDays],[Planned End]-TODAY(),0)))